## TIBER-EU Readiness Checklist
TIBER-EU ENGAGEMENT READINESS CHECKLIST
For organisations preparing for their first TIBER-EU engagement · ThreatInsights
# | Checklist Item | Status | Priority | Notes / Owner
GOVERNANCE & PREPARATION
1 | Form your White Team — the internal oversight group managing the engagement. Must be fully separate from the Blue Team (SOC) and have no operational security role. | Not Started | Critical
2 | Identify your White Team Lead — a senior individual (CISO or equivalent) with board-level authority to manage the engagement and sign off on key decisions. | Not Started | Gov
3 | Notify your national competent authority (regulator) of intent to conduct a TIBER-EU engagement and confirm their oversight involvement and reporting requirements. | Not Started | Critical
4 | Establish a legal framework — NDAs, liability agreements, and rules of engagement contracts. Engage legal counsel with financial sector security experience. | Not Started | Gov
5 | Confirm which national TIBER variant applies (TIBER-NL, TIBER-IE, TIBER-DE, TIBER-BE, etc.) and obtain the relevant national guidance documents. | Not Started | Doc
6 | Define and document the engagement timeline — TIBER-EU engagements run 3–6+ months end-to-end. Secure internal resource commitments accordingly. | Not Started | Gov
SCOPING & CRITICAL FUNCTIONS
7 | Define your Critical Functions (CFs) — the business processes whose disruption would cause systemic impact to financial stability. These drive the entire engagement scope. | Not Started | Critical
8 | Map all supporting systems, infrastructure, and third-party dependencies for each Critical Function. Red team will target live production systems underpinning these. | Not Started | Doc
9 | Document your Crown Jewels — assets, data stores, and systems that represent the highest-impact compromise scenario for an adversary. | Not Started | Doc
10 | Establish explicit deconfliction procedures — agree the process for real incident vs. exercise disambiguation including escalation contacts and out-of-band communication channels. | Not Started | Critical
11 | Confirm that live production systems will be in scope — TIBER-EU does not permit testing against staging or test environments. | Not Started | Critical
PROVIDER SELECTION
12 | Select an accredited Threat Intelligence Service Provider (TISP) — confirm accreditation status with your national competent authority. Must be independent from the Red Team. | Not Started | Critical
13 | Select an accredited Red Team Service Provider (RTSP) — separately procured from the TISP. Request evidence of prior TIBER-EU engagements and relevant accreditation. | Not Started | Critical
14 | Confirm neither provider has had access to your internal systems in the past 12 months — this would compromise the integrity of the exercise. | Not Started | Critical
15 | Validate RTSP team members can meet any vetting or clearance requirements stipulated by your security policy or jurisdiction. | Not Started | Gov
16 | Confirm that a single provider is NOT being used for both TISP and RTSP roles — this is prohibited under the TIBER-EU framework. | Not Started | Critical
THREAT INTELLIGENCE READINESS
17 | Prepare the Scope Document to provide to the TISP — defines the entity, critical functions, relevant geographies, and assets in scope for intelligence collection. | Not Started | Doc
18 | Conduct an internal threat profile review — understand who your real adversaries are before the TISP starts. Prior CTI reporting, incident history, and sector intelligence all feed this. | Not Started | Doc
19 | Audit your external attack surface — domain portfolio, certificate transparency logs, exposed infrastructure, and credential exposure on dark web sources. The TISP will find this. | Not Started | Critical
20 | Review supply chain dependencies — third-party access to critical systems, managed service providers, and cloud platform dependencies that may represent initial access vectors. | Not Started | Doc
21 | Ensure your CTI team or CTI function can consume and validate the Targeted Threat Intelligence Report (TTIR) produced by the TISP before handoff to the Red Team. | Not Started | Doc
BLUE TEAM & SOC READINESS
22 | Confirm your SOC and Blue Team are fully operational and unaware of the engagement — their authentic, unprimed detection and response is what is being tested. | Not Started | Critical
23 | Verify SIEM, EDR, and logging infrastructure are fully operational and retaining sufficient log history (minimum 90 days recommended) prior to engagement start. | Not Started | Critical
24 | Ensure detection use cases and alert thresholds are not artificially tuned or enhanced ahead of the engagement — this invalidates the SOC detection findings. | Not Started | Critical
25 | Plan for the Purple Team exercise at closure — schedule time post-exercise for the structured debrief where Red and Blue work through findings together. | Not Started | Doc
POST-ENGAGEMENT & ATTESTATION
26 | Prepare a remediation tracking structure before the engagement ends — TIBER-EU requires a formal remediation plan and regulators will ask about progress at attestation. | Not Started | Gov
27 | Understand the attestation process for your national variant — the Test Report and remediation status are shared with the competent authority, not retained internally. | Not Started | Gov
28 | Schedule a lessons-learned review with your White Team, RTSP, and TISP to capture process improvements for future engagements. | Not Started | Doc
29 | Feed Purple Team findings directly into your detection engineering backlog — each undetected TTP should become a tuning or rule-creation task for your SOC. | Not Started | Critical
Total items: 29 |  | 0 | 0 of 29 complete (0%)
PRIORITY KEY: Critical = stop-work if not resolved · Doc = documentation / preparation artefact required · Gov = governance / legal / regulatory action